## Sheet1
Customer					Admin

Tasks Name	Start / Build	Finish / Build	% / Build	Names	Notes		Tasks Name	Start / Build	Finish / Build	% / Build	Names	Notes
Header	21/8	08/23	100%	Ryan Tieu			Header	08/24	27/8	100%	Ryan Tieu
Main logo	21/8	08/23	100%	Ryan Tieu			Sidebar	08/24	27/8	100%	Ryan Tieu
Searchbar	21/8	08/23	100%	Ryan Tieu			Product Table	08/27	29/8	100%	Ryan Tieu
Account logo	21/8	08/23	100%	Ryan Tieu			Product Creation Form	08/27	29/8	100%	Ryan Tieu
Shopping cart logo	21/8	08/23	100%	Ryan Tieu			Update Modal	08/29	08/31	100%	Ryan Tieu
Sidebar	21/8	08/23	100%	Ryan Tieu			Add Modal	08/29	08/31	100%	Ryan Tieu
Filter	03/09	03/09	100%	Ryan Tieu			Search Feature	08/29	08/31	100%	Ryan Tieu
Product Grid	08/23	08/23	100%	Ryan Tieu			Filtering Feature	08/29	08/31	100%	Ryan Tieu
Product Overview	23/8	24/8	100%	Ryan Tieu
Shopping Cart	31/8	2/9	100%	Ryan Tieu
Breadcrumb	31/8	2/9	100%	Ryan Tieu
Filter Feature	2/9	3/9	100%	Ryan Tieu
Search Feature	2/9	3/9	100%	Ryan Tieu